## Summary
Procurement Plan - Content
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Summary Sheet
No | Name of the Zones, Industrial Parks , Special Projects Etc | Page Number
A | Existing Zones
1 | Katunayake Export Processing Zone | 04,05
2 | Biyagama Export Processing Zone | 06,07
3 | Koggala Export Processing Zone | 08
4 | Kandy Industrial Park | 09
5 | Malwatta Export Processing Park | 10
6 | Mirigama Export Processing Zone | 11
7 | Wathupitiwela Export Processing Zone | 12
8 | Horana Export Processing Zone | 13
9 | Mawathagama Export Processing Zone | 14
10 | Polgahawela Export Processing Zone | 15
11 | Mirijjawila Export Processing Zone | 16
12 | Seethawake Export Processing Zone | 17
13 | Proposed Industrial Zone Wagawatta | 18
B | New Zones
14 | Preliminary work of sites identified for new Zones. | 19
15 | Bingiriya Export Processing Zone | 20
16 | Textile Manufacturing Zone at Eravur,Batticaloa | 21
17 | Pharmaceutical Manufacturing Zone at Arabokka. | 22
18 | Site Identified for Arabokka Heavy Industry Zone | 23
C | Others
19 | Finance Department | 24
20 | Equipment for Information Technology Department | 25
21 | Contingencies - Urgent Mechanical/Electrical/Plant and Equipment. | 26
22 | Equipment for Environment Management Department | 27
23 | Administration Department | 28

## Acronyms
ACRONYMS
ICB | International Competitive Bidding
LIB | Limited International Bidding
LND | Limited National Bidding
NCB | National Competitive Bidding
NS | National Shopping
RPC | Regional Procurement Committee
DPC | Department Procurement Committee
MPC | Ministry Procurement Committee
CAPC | Cabinet Appointed Procurement Committee
DCPC | Department Consultant Procurement Committee

## PP 2024
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka

## KEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Katunayake Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
01.01 | Roads, Drains and Culverts
01.01.025 | Construction of Access Road to reclaimed land at Phase IV | 70 |  | 40 | BOI Funds | NCB | DPC | P | Assigned consultancy work to the RDA & designing, estimating & Preparing Bid doc is pending at RDA | 2023-02-03 | 30/09/2024 | 2024-07-10
01.01.026 | Improvement of drains and culverts at phase I and II. | 60 | 20 |  | BOI Funds | NCB | DPC | P | Evaluation of Bids | 2023-10-05 | 2024-02-05 | 2024-09-05
| Sub Total | 130 | 20 | 40
01.02 | Water supply
01.02.031 | Re-laying deteriorated water distribution lines at Ring road 01 and spur road 2 ,phase 1 | 250 | 1.5 |  | BOI Funds | NCB | MPC | U | Draft bid document evaluation | 2023-02-01 | 29/11/2024 | 16/12/2024
01.02.034 | Supply,laying and commissioning of water supply line for Phase lV | 75 |  | 13 | BOI Funds | NCB | DPC | P | Estimate is being revised | 27/02/2023 | 30/10/2024 | 2024-06-11
01.02.035 | Supply and installation of Gate valves/ Sluice valves and washout valves | 2.5 | 2.5 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2024-01-01 | 30/05/2024 | 2024-06-06
01.02.036 | Supply and installation of Bulk water Meters for all Phases | 10 | 8 |  | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 2024-01-01 | 30/05/2024 | 2024-06-06
| Sub Total | 337.5 | 12 | 13
01.03 | Sewerage/Wastewater Treatment
01.03.026 | Supply,laying and commissioning of wastewater disposal pumping line form Phase lV to CWWTP | 100 |  | 15 | BOI Funds | NCB | DPC | P | Dept. estimate approved | 2023-02-03 | 30/10/2024 | 13/11/2024
01.03.027 | Supply and installation of belt press machine | 10 |  | 8 | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 2024-01-01 | 28/06/2024 | 2024-05-07
| Sub Total | 110 |  | 23
01.04 | Power supply
01.04.014 | Extension of Electricity line to reclaimed land at Phase IV | 3.5 |  | 2 | BOI Funds | DC |  | U | Entrusted to CEB | 2023-02-01 | 2024-04-06 | 2024-11-06
01.04.015 | Rearrange of power supply connections to Administration building,Plaza unit 01 to 06 Fire unit and gate 01 | 42 | 8 |  | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 15/12/2023 | 30/10/2024 | 2024-06-11
01.04.016 | Supply and installation of 02 nos 22KW VFD panels including Sensor based PLC operation of 12 nos aerators at CWWTP | 13 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2024-01-01 | 28/06/2024 | 2024-05-07
01.04.017 | Supply and installation of Solar power generation system for Gate 01 and Gate 04 of BOI-KEPZ. | 30 |  | 8 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 2024-01-03 | 30/07/2024 | 2024-06-08
| Sub Total | 88.5 | 13 | 10
01.05 | Buildings
01.05.051 | Renovation of roof at security and custom Gate 01 | 5 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 15/12/2023 | 30/05/2024 | 2024-06-06
01.05.052 | Repair of Fire Unit at Gate 1 (VIP Entrance) | 8 | 6 |  | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 15/12/2023 | 28/06/2024 | 2024-05-07
01.05.053 | Refurbishment of Engineering, IR, Finance & Audit at Plaza buildings | 20 | 8 |  | BOI Funds | NCB | DPC | N | Dept. estimate prepared | 2023-01-03 | 31/05/2024 | 2024-07-06
01.05.054 | Construction of compost yard | 8.5 |  | 8.5 | BOI Funds | NCB | DPC | U | Dept. estimate prepared | 15/12/2023 | 30/04/2024 | 2024-07-05
| Sub Total | 41.5 | 19 | 8.5
01.08 | Fencing
01.08.010 | Improvement of peripheral fence at Phase 1 and Phase 2 | 40 | 15 |  | BOI Funds | NCB | DPC | P | Evaluation of Bids | 27/06/2023 | 30/04/2024 | 2024-07-05
| Sub Total | 40 | 15
01.09 | Miscellaneous
01.09.042 | Installation of CCTV surveillance system at all gates of KEPZ | 17.3 |  | 17 | BOI Funds | NCB | DPC | U | Draft Bid document is in the process of approval | 2023-01-03 | 31/05/2024 | 2024-07-06
01.09.039 | Supply, Installation and Maintenance of E-Access Control System for enetrance of KEPZ | 25 |  | 1 | BOI Funds | NCB | DPC | N | Consultancy assignment been done by University of Moratuwa. | 15/12/2023 | 2024-02-05 | 2024-09-05
01.09.046 | Supply and fabrication of 02 nos of new tractor trailers and covers | 2 |  | 2 | BOI Funds | LNB | DPC | U | Quotations to be invited | 20/12/2023 | 28/06/2024 | 2024-04-07
01.09.045 | Surveying. | 1 | 1 |  | BOI Funds |  |  | U | Surveying to be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 45.3 | 1 | 20
| Total Amount | 792.8 | 80 | 114.5
As at 01/01/2024

## BEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Biyagama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) ( Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
02.01 | Roads, Drains and Culverts
02.01.022 | Construction of storm water drain from abandoned quarry located within BEPZ zonal area to Yabaraluwa Public Ground | 14.6 |  | 12.6 | BOI Funds | DC |  | U | Board approval received. MOU to be signed with DS- Gampaha | 2023-01-10 | 30/04//2024 | 2024-07-05
02.01.023 | Improvements to the vehicle park at Permit office and Entrance of Fire Building | 4 | 4 |  | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 2023-01-02 | 2024-02-07 | 2024-09-07
02.01.024 | Construction of storm water drain along the internal road of Block A at BEPZ | 5 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 2024-03-06 | 15/10/2024 | 22/10/2024
| Sub Total | 23.6 | 9 | 12.6
02.03 | Sewerage / Wastewater Treatment
02.03.033 | Construction of outfall structure and balance part of treated effluent pumping main of the proposed interceptor sewer line from Biyagama Export Processing Zone | 119.2 | 65 |  | BOI Funds | NCB | DPC | U | Bid Evaluation | 29/08/2023 | 30/05/2024 | 13/06/2024
02.03.035 | Augmentation of CWWTP-BEPZ - Consultancy | 5 | 5 |  | BOI Funds | DC |  | P | Preliminary design to be prepared by NWS&DB | 15/05/2024 | 14/11/2024 | 21/11/2024
| Sub Total | 124.2 | 70
02.04 | Power Supply
02.04.009 | Supply & Installation of a 250 kVA Generator to Administration Building BEPZ | 18.5 |  | 13 | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 18/03/2024 | 30/08/2024 | 2024-06-09
02.04.010 | Improvements to the existing Street Light network with HT & LT bundle cables & poles of internal Roads at Block ‘A’ BEPZ | 8 | 8 |  | BOI Funds | NCB | DPC | U | Estimate to be obtained from CEB | 22/04/2024 | 2024-03-09 | 2024-10-09
| Sub Total | 26.5 | 8 | 13
02.05 | Building
02.05.023 | Construction of Security Room for Lift Station of KRB II in CWWTP at BEPZ | 3 | 2 |  | BOI Funds | NCB | DPC | U | Dept. Estimate is being scrutinized | 15/11/2023 | 2024-02-05 | 2024-09-05
02.05.024 | Improvement to the two storied Fire & Security Building at BEPZ | 10.5 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 15/03/2024 | 30/08/2024 | 2024-06-09
02.05.026 | Supply & Installation of a 07 Nos Split type Air-conditioning to Admin Building, Fire office & Security Building of Main Gate at BEPZ | 7 | 7 |  | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 15/02/2024 | 25/05/2024 | 2024-03-06
| Sub Total | 20.5 | 14
02.09 | Miscellaneous
02.09.019 | Improvements of old dump yard at BEPZ | 5 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 19/04/2024 | 30/08/2024 | 2024-06-07
| Sub Total | 5 | 5
| Total Amount | 199.8 | 106 | 25.6
As at 01/01/2024

## KgEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Koggala Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
03.01 | Roads, Drains and Culverts
03.01.020 | Construction of balance part of P11P12P13 road - including consultancy charges for RDA | 24.5 | 15 |  | BOI Funds | NCB | DPC | U | Evaluation of bids | 2023-01-10 | 2024-03-06 | 2024-10-06
03.01.021 | Construction of storm water drainage system at Star Garments (Pvt) Ltd | 2 | 2 |  | BOI Funds | NCB | RPC | N | Estimate to be prepared | 2024-01-05 | 30/08/2024 | 2024-06-09
| Sub Total | 26.5 | 17
03.02 | Water Supply
03.02..018 | Construction of 1000m3 capacity ground water sump | 128 |  | 20 | BOI Funds | NCB | DPC | U | Investigation & preliminary design completed by NWSDB | 2023-02-10 | 2024-01-10 | 2024-11-11
| Sub Total | 128 |  | 20
03.03 | Sewerage / Wastewater Treatment
03.03.016 | Construction of new sea outfall line | 140 | 50 |  | BOI Funds | NCB | DPC | U | PC instructed to revise the estimate & retender . | 2021-06-01 | 2024-10-10 | 24/10/2024
03.03.030 | Repairs to the Package Treatment Plant including the consultancy charges of NWSDB | 7.5 | 1 |  | BOI Funds | NCB | DPC | U | Estimate to be received from NWSDB | 2024-03-06 | 29/11/2024 | 2024-06-12
| Sub Total | 147.5 | 51
03.05 | Building
03.05.022 | Construction of toilets & washrooms to the use of workers at water supply scheme and to the 2nd gate security building-KgEPZ | 2 | 2 |  | BOI Funds | NCB | DPC | U | Contract to be awarded | 27/02/2023 | 31/01/2024 | 2024-07-02
03.05.023 | Construct poly carbonate shelter over the sludge drying beds | 2.5 | 2 |  | BOI Funds | NS | DPC | N | Estimate to be prepared | 15/03/2024 | 15/05/2024 | 27/05/2024
| Sub Total | 4.5 | 4
| Total Amount | 306.5 | 72 | 20
As at 01/01/2024

## KIP
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Kandy Industrial Park
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
04.01 | Roads Drains & Culverts
04.01.011 | Improvements to R2 and R4 internal roads. | 7.5 |  | 7.5 | BOI Funds | NCB | DPC | U | Evaluation of Bids | 2023-02-03 | 2024-01-03 | 2024-11-03
04.01.014 | Preliminary gravel road design and construction work for the 14 Ac land (KTI) | 75 |  | 7.5 | BOI Funds | NCB | DPC | P | Designing & planning | 2024-05-04 | 2024-03-09 | 2024-10-09
| Sub Total | 82.5 |  | 15
04.05 | Building
04.05.010 | Construction of a buildings for Fire Department. | 2 |  | 1.5 | BOI Funds | NCB | DPC | U | PC approval granted to Contract award after obtaining clarifications from the lowest bidder | 2023-12-08 | 15/02/2024 | 26/02/2024
04.05.011 | Construction of a buildings for Sathosa outlet | 3 |  | 1 | BOI Funds | NCB | DPC | N | Designing & planning | 30/03/2024 | 30/09/2024 | 2024-06-10
04.05.012 | Construction of Plant Operator Room with Sanitary Facilities. | 2.5 |  | 2.5 | BOI Funds | NCB | DPC | U | Designing & planning | 2024-02-04 | 30/07/2024 | 2024-07-08
| Sub Total | 7.5 |  | 5
04.09 | Miscellaneous
04.09.009 | Supply, installation ,commissioning and maintenance of nos 10 of surveillance CCTV cameras to cover the main gate building and vehicle park | 2.5 |  | 2.5 | BOI Funds | NCB | DPC | U | Evaluation of Bids | 17/04/2023 | 20/03/2024 | 2024-01-04
04.09.010 | Survey works, valuation and other consultancy charges. | 1 | 1 |  | BOI Funds |  |  | U | Surveying to be done as required | 2024-01-01 | 31/12/2024
04.09.011 | Soil Investigations for the 14 Ac land (KTI) | 0.5 |  | 0.5 | BOI Funds | NS | DPC | P | Planning and estimation to be commenced | 2024-05-03 | 25/07/2024 | 2024-01-08
04.09.012 | Jungle clearing, removing high grown bushes, cutting trees ,etc for the 14 Ac land (KTI) | 0.5 |  | 0.5 | BOI Funds | NCB | DPC | P | Planning and estimation to be commenced | 2024-01-03 | 25/07/2024 | 2024-01-08
04.09.013 | EIA Related work for the 14 Ac land (KTI) | 0.5 |  | 0.5 | BOI Funds | NS | DPC | P | Planning and estimation to be commenced | 25/03/2024 | 30/08/2024 | 2024-06-09
| Sub Total | 5 | 1 | 4
04.11 | Land Development
04.11.001 | Land Development for 14 Ac. land (KTI). | 10 |  | 5 | BOI Funds | NCB | DPC | P | Planning and estimation to be commenced | 25/04/2024 | 25/09/2024 | 2024-02-10
| Sub Total | 10 |  | 5
| Total Amount | 105 | 1 | 29
As at 01/01/2024

## MEPP
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Malwatta Export Processing Park
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
05.03 | Sewerage / Wastewater Treatment
05.03.010 | Supply and installation of 04 nos of lift well pumps for lift station 1 and 2 of Wastewater Treatment Plant and thrash rack , Including construction supervision. | 19.5 | 12.5 |  | BOI Funds | NCB | DPC | U | Bids to be invited | 2022-01-02 | 18/06/2024 | 25/06/2024
| Sub Total | 19.5 | 12.5
05.05 | Building
05.05.013 | Replacing of Existing Gutters & Downpipes for BOI Admin Building | 1.5 | 1.5 |  | BOI Funds | NS | DPC | P | Estimate to be prepared | 2024-01-02 | 31/05/2024 | 2024-07-06
05.05.014 | Improvement to the Washrooms for Security Office Near Gate 2 & Labor Rest Area Near BOI Admin Building. | 0.5 | 0.5 |  | BOI Funds | NS | DPC | P | Estimate to be prepared | 2024-01-03 | 2024-03-06 | 2024-10-06
| Sub Total | 2 | 2
| Total Amount | 21.5 | 14.5
As at 01/01/2024

## MEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Mirigama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
06.01 | Roads, Drains and Culverts
06.01.044 | Construction of access roads to Water Treatment Plant . | 5 | 2 |  | BOI Funds | NCB | DPC | U | Estimate is being revised according to new market rates. | 15/02/2023 | 2024-01-10 | 2024-08-10
06.01.045 | Renovation of access road to water loading bay and Repair of internal road at Block A from Lot No.29B to 27B . | 3.5 | 3.5 |  | BOI Funds | NCB | DPC | U | Amalgamating previously prepared estimates. | 2023-01-12 | 30/08/2024 | 2024-06-09
| Sub Total | 8.5 | 5.5
06.02 | Water Supply
06.02.019 | Supply, installation & Commissioning of high lift pumps for Water treatment plant. | 29.5 | 21.5 |  | BOI Funds | NCB | DPC | U | Revised estimate is in the process of approval | 15/02/2023 | 15/07/2024 | 22/07/2024
| Sub Total | 29.5 | 21.5
06.03 | Sewerage / Wastewater Treatment
06.03.007 | Design Consultancy investigation & Construction supervision of laying sewer collection network of block A. | 16 |  | 6 | BOI Funds | DC |  | P | Estimate is being revised . | 2023-10-11 | 30/08/2024 | 2024-06-09
06.03.013 | Supplying & Laying of Sewerage Collecting network and construction of lift wells in block A of MEPZ. | 205 |  | 90 | BOI Funds | NCB | MPC | U | Evaluation of draft bidding document | 15/02/2023 | 2024-01-09 | 14/09/2024
06.03.012 | Repair and service of M & E works in WWTP. | 21 | 5 |  | BOI Funds | NCB | DPC | U | Revised estimate is in the process of approval | 15/01/2023 | 15/08/2024 | 22/08/2024
| Sub Total | 242 | 5 | 96
06.04 | Power Supply
06.04.002 | Fixing lightning arrestors to the admin building | 2.5 | 2.5 |  | BOI Funds | NCB | DPC | U | Revised estimate is in the process of approval | 15/02/2023 | 15/05/2024 | 22/05/2024
06.04.009 | Supply & commissioning of 200KVA generator for water treatment plant. | 20 |  | 6 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2024-01-03 | 2024-01-08 | 2024-08-08
| Sub Total | 22.5 | 2.5 | 6
06.05 | Building
06.05.022 | Renovation of facia boards of existing roof of administrative building at MEPZ. | 2 | 2 |  | BOI Funds | NCB | DPC | U | Contract to be awarded | 2023-10-02 | 31/01/2024 | 2024-08-02
06.05.024 | Construction of extension to the workers rest room | 6 | 4 |  | BOI Funds | NCB | DPC | U | Designing and estimation to be commenced | 15/04/2024 | 15/08/2024 | 22/08/2024
| Sub Total | 8 | 6
06.09 | Miscellaneous
06.09.022 | Supply and installation of CCTV cameras to the security points and office premises at MEPZ. | 2.1 |  | 2.1 | BOI Funds | NCB | DPC | N | Evaluate Bids | 2023-02-05 | 2024-02-04 | 2024-09-04
| Sub Total | 2.1 |  | 2.1
| Total Amount | 312.6 | 40.5 | 104.1
As at 01/01/2024

## WEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Wathupitiwala Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
07.03 | Sewerage / Wastewater Treatment
07.03.024 | Supply & Installation of Pumps & Panel Boards and Screeners to Lift Wells at Wastewater Treatment Scheme of WEPZ | 33.5 |  | 29 | BOI Funds | NCB | DPC | U | Evaluation of draft bidding document | 15/01/2023 | 30/05/2024 | 2024-06-06
| Sub Total | 33.5 |  | 29
07.05 | Building
07.05.031 | Construction of upper floor of finance department at WEPZ | 11.68 |  | 9 | BOI Funds | NCB | DPC | U | Bid evaluation | 30/06/2023 | 30/04/2024 | 2024-07-05
07.05.032 | Improvements to security buildings at main entrance of Block -A | 8 |  | 2 | BOI Funds | NCB | DPC | U | Planning and estimation to be commenced | 25/02/2024 | 25/09/2024 | 2024-01-09
07.05.033 | Construction of environment lab at upper floor of admin. building | 4 |  | 4 | BOI Funds | NCB | DPC | U | Planning and designing to be commenced | 15/02/2024 | 29/06/2024 | 2024-05-07
| Sub Total | 23.68 |  | 15
07.09 | Miscellaneous
07.09.012 | Establishing of a Central Record Room for BOI departments at WEPZ | 15 | 2 |  | BOI Funds | NCB | DPC | P | Planning and estimation to be commenced | 15/03/2024 | 18/09/2024 | 25/09/2024
| Sub Total | 15 | 2
| Total Amount | 72.18 | 2 | 44
As at 01/01/2024

## HEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Horana Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
08.02 | Water Supply
08.02.036 | Augmentation of Water Treatment Plant - Construction and Consultancy. | 565 |  | 25 | BOI Funds | NCB | CAPC | U | Document evaluation . | 2021-01-01 | 2024-12-11 | 26/11/2024
08.02.040 | Design,Supply,Installation and Commission of a floating intake | 200 |  | 75 | BOI Funds | NCB | MPC | U | Revised estimate is in the process of approval | 2022-01-02 | 2024-11-09 | 25/09/2024
08.02.041 | Construction of concrete wall to support concrete structure at Kalu Ganga water intake. | 3 | 3 |  | BOI Funds | NCB | DPC | U | Estimate is in the process of approval | 26/05/2023 | 20/05/2024 | 27/05/2024
08.02.042 | Supply and installation 01 no. Submersible Pump with motor for Pontoon 2 & 02 no. Submersible Pumps for Pontoon 1 | 4.2 | 4.2 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2023-01-11 | 2024-02-05 | 2024-09-05
08.02.043 | Supply of 4 nos chemical dosing pump for water treatment plant. | 1.5 | 1.5 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 30/11/2023 | 30/04/2024 | 2024-07-04
| Sub Total | 773.7 | 8.7 | 100
08.03 | Sewerage / Wastewater treatment
08.03.021 | Augmentation of CWWTP construction | 1110 |  | 150 | BOI Funds | NCB | CAPC | U | Document evaluation . | 2021-01-03 | 2024-07-10 | 21/10/2024
08.03.032 | Rectification of existing roof of WWTP | 10 | 7 |  | BOI Funds | NCB | DPC | U | Invitation of bids | 28/04/2023 | 15/04/2024 | 22/04/2024
08.03.033 | Improvements of intake well of Wastewater treatment plant at HEPZ | 10.72 | 8 |  | BOI Funds | NCB | DPC | U | Document evaluation | 28/02/2023 | 20/05/2024 | 27/05/2024
08.03.034 | Rectification of Rotating Immerse Disk (RID) at WWTP | 3.5 | 3.5 |  | BOI Funds | NS | DPC | U | Document evaluation | 2023-10-03 | 2024-02-05 | 2024-09-05
| Sub Total | 1134.22 | 18.5 | 150
08.05 | Building
08.05.019 | Construction of generator rooms & Purchasing of generator (02nos) at WTP & Water Intake at HEPZ. | 30 |  | 7 | BOI Funds | NCB | DPC | U | Estimate is in the process of approval | 2023-03-02 | 2024-01-08 | 15/05/2024
08.05.021 | Construction of security room at Gate 2 and construction of Security gate and security room near the CEB Grid. | 5 |  | 1.5 | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2023-05-12 | 20/08/2024 | 27/08/2024
| Sub Total | 35 |  | 8.5
08.08 | Fencing
08.08.006 | Expansion of perimeter fence. | 14.12 | 10.6 |  | BOI Funds | NCB | DPC | U | Supplementary TEC report to be submitted for PC approval | 2022-06-04 | 2024-12-11 | 27/02/2024
| Sub Total | 14.12 | 10.6
| Total Amount | 1957.04 | 37.8 | 258.5
As at 01/01/2024

## MWEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Mawathagama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
09.01 | Roads, Drains and Culverts
09.01.020 | Construction of ring road at Mawathagama EPZ. | 2 |  | 2 | BOI Funds | NS | DPC | P | Estimate approved, Bid document preparation | 2023-01-09 | 30/04/2024 | 2024-07-04
| Sub Total | 2 |  | 2
09.03 | Sewerage / Wastewater Treatment
09.03.013 | Spare pumps for Wastewater Treatment Plant- 02 nos. | 2 | 2 |  | BOI Funds | NS | DPC | P | Draft bid document preparation | 15/12/2023 | 30/04/2024 | 2024-07-04
| Sub Total | 2 | 2
09.03 | Miscellaneous
09.09.010 | CCTV facility to the main gate & in front of the office | 0.8 |  | 0.8 | BOI Funds | NS | DPC | P | Invitation of Bids | 15/02/2023 | 28/03/2024 | 2024-04-04
| Sub Total | 0.8 |  | 0.8
| Total Amount | 4.8 | 2 | 2.8
As at 01/01/2024

## PwEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Polgahawela Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
10.02 | Water Supply
10.02.012 | Supply and installation of an inline booster pump to water supply line to extended area | 1.5 | 1.5 |  | BOI Funds | NCB | DPC | U | Departmental Estimate to be prepared | 2024-01-03 | 2024-03-06 | 2024-10-06
| Sub Total | 1.5 | 1.5
10.05 | Building
10.05.006 | Consultancy services for extension of Admin building with auditorium | 2 |  | 2 | BOI Funds | NCB | DPC | U | Planning and designing to be done | 2024-02-05 | 2024-01-08 | 08/082024
| Sub Total | 2 |  | 2
10.09 | Miscellaneous
10.09.010 | Construction of Gabion walls for eroded river bank area in rear side of Lot No.1C (part iv ) | 6 |  | 5 | BOI Funds | NCB | DPC | U | PC instructed to retender. Revised bidding document to be submitted for PC approval. | 15/01/2024 | 20/06/2024 | 27/06/2024
10.09.012 | Supply and installation of CCTV system | 1.5 |  | 1.5 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 2024-02-04 | 31/07/2024 | 2024-08-08
10.09.013 | Improvements to the flood protection bund | 7 | 7 |  | BOI Funds | NCB | DPC | U | Planning and designing to be done | 2024-01-02 | 31/05/2024 | 2024-07-06
| Sub Total | 14.5 | 7 | 6.5
| Total Amount | 18 | 8.5 | 8.5
As at 01/01/2024

## MjEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Mirijjawila Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB, NCB and National Shopping etc.) | Level of Authority | Priority Status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
13.01 | Roads, Drains and Culverts
13.01.015 | Main entrance road to MjEPZ along the boundary of RN Innovations Construction (Pvt) Ltd. | 50 |  | 45 | BOI Funds | NCB | DPC | P | Invitation of Bids | 27/02/2023 | 15/05/2024 | 22/05/2024
13.01.016 | Rectification of damaged sections to main entrance road CH 0+00 to CH 0+218) | 5 | 5 |  | BOI Funds | NCB | DPC | U | Re-tendering | 2023-02-03 | 30/04/2024 | 2024-07-04
| Sub Total | 55 | 5 | 45
13.02 | Water Supply
13.02.007 | Improvements to the existing Water Tower & Sump. | 25 | 20 |  | BOI Funds | NCB | DPC | N | Draft bid document is been prepared by NWSDB | 30/03/2022 | 18/06/2024 | 25/06/2024
| Sub Total | 25 | 20
13.05 | Building
13.05.009 | Expansion and Renovation of existing zonal Administrative Building | 12 | 8 |  | BOI Funds | NCB | DPC | U | Bids to be invited | 2022-10-11 | 20/06/2024 | 27/06/2024
13.05.010 | Security and gate facilities at the rear boundary road entrance | 2.5 |  | 2.5 | BOI Funds | NCB | DPC | N | Designing and estimation to be done | 31/01/2024 | 30/05/2024 | 2024-06-06
13.05.011 | Supply and installation of a generator for office building | 7 |  | 2 | BOI Funds | NCB | DPC | N | Designing and estimation to be done | 15/02/2024 | 15/06/2024 | 13/06/2024
| Sub Total | 21.5 | 8 | 4.5
13.09 | Miscellaneous
13.09.010 | Survey works & other consultancy services. | 2.5 | 2.5 |  | BOI Funds |  |  |  | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 2.5 | 2.5
| Total Amount | 104 | 35.5 | 49.5
As at 01/01/2024

## SEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Seethawake Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
23.02 | Water Supply
23.02.022 | Supply & Installation of VSD for the transmission pumps at WTP. | 5 | 5 |  | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2023-01-11 | 2024-04-03 | 2024-11-03
23.02.025 | Supply & Installation of the reservoir outlet valve (450 mm Diameter.) | 5 | 5 |  | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 16/11/2023 | 30/03/2024 | 2024-05-04
23.02.026 | Rectification of the defects in the package water treatment plant | 8 | 8 |  | BOI Funds | NCB | DPC | P | Dept. estimate prepared | 2023-01-11 | 2024-04-04 | 15/04/2024
23.02.027 | Supply of Electrical Driven Submersible Pumps -03 Nos and Accessories | 6 |  | 6 | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 20/11/2023 | 25/04/2024 | 2024-03-05
23.02.028 | Modification of the Chlorine safety system | 5 |  | 3 | BOI Funds | NCB | DPC | P | Dept. estimate is being prepared | 2023-04-12 | 2024-02-05 | 2024-09-05
| Sub Total | 29 | 18 | 9
23.05 | Building
23.05.037 | Renovation of Office Building /roof and toilets at WTP & WWTP | 3 | 3 |  | BOI Funds | NCB | DPC | N | Dept. estimate is being prepared | 2023-01-12 | 2024-02-05 | 2024-09-05
23.05.038 | Construction of roof of the Daycare Center Building | 4 | 4 |  | BOI Funds | NCB | DPC | N | Dept. estimate is being prepared | 2023-03-10 | 18/04/2024 | 25/04/2024
23.05.039 | Expansion of Director's rest room | 1.5 | 1.5 |  | BOI Funds | NCB | DPC | N | Dept. estimate prepared | 2023-05-10 | 18/04/2024 | 25/04/2024
| Sub Total | 8.5 | 8.5
| Total Amount | 37.5 | 26.5 | 9
As at 01/01/2024

## WIZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Wagawatta Industrial Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
33.01 | Roads, Drains and Culverts
33.01.019 | Leadway drain from Internal boundary road up to Arunagama road. | 8 | 8 |  | BOI Funds | NCB | DPC | P | Draft Bidding document to be submitted for PC-approval | 2022-07-07 | 28/07/2024 | 2024-05-08
33.01.021 | Rectification of storm water drains outside the Wagawatta Industrial Zone including consultancy | 2 | 1 |  | BOI Funds | DC | DPC | P | Requesting consultancy and estimating from Agrarian Services Kalutara. | 30/12/2022 | 25/07/2024 | 2024-01-08
| Sub Total | 10 | 9
33.09 | Miscellaneous
33.09.009 | Land acquisition | 1 | 1 |  | BOI Funds | DC |  | N | To be done as required | 28/02/2023 | 30/06/2024 | 2024-08-07
33.09.010 | Construction of Security main gate | 2 |  | 2 | BOI Funds | NCB | DPC | U | Dept. estimate is being prepared | 2023-10-12 | 2024-10-07 | 17/07/2024
| Sub Total | 3 | 1 | 2
| Total Amount | 13 | 10 | 2
As at 01/01/2024

## NZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Preliminary work of sites identified for new Zones.
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
69.01 | Roads, Drains and Culverts
69.01.006 | Preliminary access road construction work. | 10 |  | 3 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 15/05/2024 | 30/12/2024 | 30/12/2024
| Sub Total | 10 |  | 3
69.02 | Water Supply
69.02.008 | Initial Water Supply. | 20 |  | 5 | BOI Funds | DC |  | P | To be entrusted to NWSDB/WRB | 15/07/2024 | 22/11/2024
69.02.009 | Ground water investigation | 10 |  | 4 | BOI Funds | DC |  | P | To be entrusted to NWSDB/WRB | 18/06/2024 | 30/10/2024
| Sub Total | 30 |  | 9
69.04 | Power Supply
69.04.007 | Initial power supply. | 5 |  | 2 | BOI Funds | DC |  | P | To be entrusted to CEB | 26/09/2024 | 30/10/2024
| Sub Total | 5 |  | 2
69.05 | Building
69.05.010 | Temporary site offices for new zones | 7.5 |  | 4 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 15/06/2024 | 29/11/2024 | 2024-05-12
69.05.011 | Temporary security points with Sanitary Facilities for new Zones | 3 |  | 2 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 15/06/2024 | 29/11/2024 | 2024-05-12
| Sub Total | 10.5 |  | 6
69.08 | Fencing
69.08.010 | Construction of a perimeter fence. | 10 |  | 2 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 2024-01-07 | 29/11/2024 | 2024-05-12
| Sub Total | 10 |  | 2
69.09 | Miscellaneous
69.09.020 | Survey works, valuation and other consultancy charges. | 20 |  | 10 | BOI Funds |  |  |  | To be done as required | 2024-01-01 | 31/12/2024
69.09.021 | Soil Investigations. | 5 |  | 2 | BOI Funds | DC |  | P | To be entrusted to NBRO | 2024-01-01 | 31/12/2024
69.09.022 | Jungle clearing, removing high grown bushes, cutting trees ,etc. | 20 |  | 5 | BOI Funds | NCB | DPC | P | Dept. estimate to be prepared | 31/03/2024 | 31/07/2024 | 2024-08-08
69.09.023 | EIA Related works | 20 |  | 5 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 65 |  | 22
69.11 | Land Acquisition
69.11.001 | Land Acquisition related works | 5 |  | 2 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 5 |  | 2
| Total Amount | 135.5 |  | 46
As at 01/01/2024

## BgEPZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Bingiriya Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
73.01 | Roads, Drains & Culverts
73.01.002 | Improvement to existing internal roads.(Stage 1 - Widening existing road No 1,6 & 7 up to sub base) | 28 |  | 20 | BOI Funds | NCB | DPC | N | Bid evaluation | 2023-02-05 | 15/02/2024 | 22/02/2024
73.01.003 | Construction of internal drain network at Bingiriya EPZ | 10 |  | 1 | BOI Funds | NCB | DPC | N | Estimating is in Progress | 2023-04-07 | 2024-01-07 | 2024-08-07
73.01.004 | Access road for CEB power line from gantry | 2.5 |  | 2 | BOI Funds | NCB | DPC | N | Estimate prepared | 2023-05-06 | 30/04/2024 | 2024-06-05
| Sub Total | 40.5 |  | 23
73.04 | Power Supply
74.04.004 | Supply & installation of street lights at Bingiriya EPZ | 3 |  | 1.5 | BOI Funds | NCB | DPC | N | Estimate to be prepared | 2024-01-02 | 2024-01-06 | 2024-07-06
73.04.002 | Gantry Construction | 30 |  | 5 | BOI Funds | DC |  | N | To be entrusted to CEB | 18/06/2024 | 30/10/2024 | 2024-06-11
| Sub Total | 33 |  | 6.5
73.05 | Building
73.05.007 | Refurbishment of existing office building (Appx.100m2) and garage for office vehicle at BgEPZ | 5 | 2 |  | BOI Funds | NCB | DPC | N | Estimate to be prepared | 30/04/2024 | 2024-02-09 | 2024-09-09
73.05.008 | Constructions of security rooms and entrance gate. | 5 |  | 1 | BOI Funds | NCB | DPC | N | Estimate to be prepared | 30/08/2024 | 16/12/2024 | 23/12/2024
| Sub Total | 10 | 2 | 1
73.08 | Fencing
73.08.003 | Constructions of balance chain link fence. | 32 |  | 1 | BOI Funds | NCB | DPC | N | Estimate to be prepared | 30/06/2024 | 18/11/2024 | 25/11/2024
| Sub Total | 32 |  | 1
73.09 | Miscellaneous
73.09.001 | Survey works, valuation and other consultancy charges | 3 |  | 3 | BOI Funds | DC |  | N | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 3 |  | 3
| Total Amount | 118.5 | 2 | 34.5
As at 01/01/2024

## TMZ
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Textile Manufacturing Zone, – Punnakuda, Eravur, Batticaloa
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated cost (Rs. Mn) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U= Urgent P= Priority N= Normal | Current status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
74.01 | Roads, Drains & Culverts
74.01.009 | Preliminary construction works of Jeep Track - Stage I | 15 |  | 3 | BOI Funds | NCB | DPC | P | Preliminary design stage | 20/03/2024 | 20/06/2024 | 27/06/2024
74.01.011 | Construction of main internal road | 61 |  | 50 | BOI Funds | NCB | DPC | U | Estimating is in Progress | 17/06/2023 | 15/07/2024 | 2024-01-08
| Sub Total | 76 |  | 53
74.02 | Water supply
74.02.004 | Permanent Internal Water Supply Scheme (Construction phase) | 267.5 |  | 20 | BOI Funds | NCB | MPC | U | Design is completed | 2024-02-01 | 2024-12-11 | 2024-02-12
74.02.007 | Construction of 3nos. shallow wells | 3 |  | 3 | BOI Funds | NS | DPC | U | Investigation reports has been submitted by WRB | 2024-02-02 | 2024-02-05 | 2024-09-05
| Sub Total | 270.5 |  | 23
74.03 | Sewerage /Wastewater Treatment
74.03.003 | Construction of wastewater collection network | 876.3 |  | 125 | BOI Funds | NCB | CAPC | U | Design of WWCN is being reviewing for some design modifications | 2024-02-01 | 20/12/2024 | 26/12/2024
| Sub Total | 876.3 |  | 125
74.04 | Power Supply
74.04.005 | Internal power supply Scheme (HT balance supply) | 4 |  | 2 | BOI Funds | DC |  | U | To be entrusted to CEB | 18/06/2024 | 30/09/2024 | 18/06/2024
74.04.007 | Internal power supply Scheme (Supply and installation of 20 nos street lights) | 1.5 |  | 1.5 | BOI Funds | NS | DPC | U | Estimate to be prepared | 2024-01-02 | 2024-02-05 | 2024-09-05
74.04.008 | Construction of a meter cubical for LT line. | 0.5 |  | 0.5 | BOI Funds | NS | DPC | U | Estimating is in Progress | 2024-01-01 | 2024-05-03 | 2024-12-03
| Sub Total | 6 |  | 4
74.05 | Building
74.05.005 | Design Consultancy for an office building | 30 |  | 3 | BOI Funds | NCB | DCPC | U | Conceptual planning | 2024-01-02 | 2024-02-07 | 2024-09-07
74.05.007 | Supply and placing of additional container box with required facilities. | 4 |  | 3.5 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 2024-01-03 | 18/06/2024 | 25/06/2024
| Sub Total | 34 |  | 6.5
74.08 | Fencing
74.08.001 | Construction of Perimeter Fence along the Boundary (200 Acres)- stage 1 | 85.5 |  | 60 | BOI Funds | NCB | DPC | U | Bids evaluation is in progress | 2023-01-08 | 31/01/2024 | 2024-06-02
74.08.003 | Construction of Perimeter Fence (1.6 km) - stage II (along the balance length of the boundary 200 & 55.28 Acres Lands) | 50 |  | 36 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 2024-02-05 | 2024-02-12 | 2024-09-12
| Sub Total | 135.5 |  | 96
74.09 | Miscellaneous
74.09.001 | Survey works, valuation and other consultancy charges. | 3 |  | 3 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
74.09.009 | EIA/IEE related works. | 5 |  | 2 | BOI Funds |  |  | U | To be done as required | 2024-01-01 | 31/12/2024
74.09.010 | Establishment of environment monitoring facilities | 5 |  | 0.5 | BOI Fund | DC |  | U | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 13 |  | 5.5
| Total Amount | 1411.3 |  | 313
As at 01/01/2024

## PHAMA
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Pharmaceutical Manufacturing Zone at Arabokka
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
Phase -2
| Construction of perimeter fence (Phase 2) | 50 |  |  | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2024-01-09 | 31/12/2025
| Construction of electric fence (Phase 2). | 25 |  |  | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2024-01-05 | 15/8/2025
| Preparation of jeep track along the perimeter boundary. | 4 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2023-01-03 | 2023-01-05
| Water connection | 20 |  |  | BOI Funds | DC |  | N | Planning stage | 2022-04-12
| Internal power supply Scheme (LT/HT supply). |  |  |  | BOI Funds | DC |  | N | Planning stage | 2022-05-10
| Construction of Meter Cubical for CEB supply. |  |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2022-05-18 | 2022-06-18
| Survey works. |  |  |  | BOI Funds | DC |  | N | Planning stage | 2022-04-01 | 2022-12-31
| Environmental Impact Assessment | 10 |  |  | BOI Funds | NCB | DPC | N | Planning stage
Phase -3 & Phase 4
| Clearing of jungle | 10 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2023-01-12 | 28/02/2024
| Construction of electric fence | 18 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2023-01-05 | 30/09/2023
| Construction of perimeter fence | 150 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2024-01-05 | 30/09/2024
| Preparation of jeep track along the perimeter boundary. | 4 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2024-01-06 | 2024-01-09
| Water connection | 2 |  |  | BOI Funds | DC |  | N | Planning stage | 2024-01-07
| Internal power supply Scheme (LT/HT supply). | 40 |  |  | BOI Funds | DC |  | N | Planning stage | 2024-01-15
| Construction of Meter Cubical for CEB supply. | 4 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2024-01-23 | 2024-02-23
| Survey works. | 10 |  |  | BOI Funds | DC |  | N | Planning stage | 2023-01-03 | 2023-12-31
| Geotechnical investigation | 3 |  |  | BOI Funds | NCB | DPC | N | Planning stage
| Environmental Impact Assessment | 10 |  |  | BOI Funds | NCB | DPC | N | Planning stage
| Construction of wastewater collection network. | 400 |  |  | BOI Funds | NCB | MPC | N | Planning stage | 2024-01-12
| Design/Construction of Administration building | 85 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 15/8/2021 | 25/12/2022
| Design Consultancy services for common wastewater treatment plant and wastewater collection network | 63 |  |  | BOI Funds | NCB | DPC | N | Planning stage | 2024-01-02 | 2024-01-05
| Construction of common wastewater treatment plant | 900 |  |  | BOI Funds | NCB | CAPC | N | Planning stage | 2024-01-12
75.01 | Roads, Drains and Culverts
75.01.007 | Access to main internal road from RDA road and culvert | 4 |  | 2 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2024-05-02 | 2024-12-06 | 19/06/2024
| Sub Total | 4 |  | 2
75.02 | Water Supply
75.02.003 | Extension of 300 cum/day water supply line with in the phase 1 zone for construction supply including design consultancy. | 8 |  | 2 | BOI Funds | DC |  | P | To be entrusted to NWSDB | 2024-10-09 | 22/11/2024 | 29/11/2024
| Sub Total | 8 |  | 2
75.04 | Power Supply
75.04.001 | Initial temporary power supply 1 MVA. | 15 |  | 2 | BOI Funds | DC |  | P | To be entrusted to CEB | 2024-02-09 | 29/11/2024 | 2024-02-09
| Sub Total | 15 |  | 2
75.09 | Miscellaneous
75.09.006 | Repairing of Existing front boundary wall & construction of Security room & gate (Phase 1) | 5 |  | 4 | BOI Funds | NCB | DPC | U | Invitation of bids | 2023-11-10 | 30/04/2024 | 2024-07-05
75.09.003 | Geotechnical investigation (Phase 2). | 2 |  | 0.5 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
75.09.004 | Survey works, valuation and other consultancy charges. | 5 |  | 1.5 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
75.09.007 | EIA and IEA related works. | 1.5 |  | 1.5 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
75.09.008 | Soil and groundwater investigation | 1 |  | 1 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 14.5 |  | 8.5
| Total Amount | 41.5 |  | 14.5
As at 01/01/2024

## ARABOKKA
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Site Identified for Arabokka Heavy Industry Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
78.01. | Roads, Drains and Culverts
78.01.001 | Preliminary gravel road construction work up to Gloves International (PVT) Ltd Land (Stage I) | 50 |  | 45 | BOI Funds | NCB | DPC | U | Invitation of bids | 20/11/2023 | 30/04/2024 | 2024-07-05
78.01.002 | Preliminary gravel road construction work.(Stage II) | 12 |  | 1 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 20/04/2024 | 30/08/2024 | 2024-06-09
| Sub Total | 62 |  | 46
78.02 | Water Supply
78.02.001 | Water supply/ connections | 25 |  | 20 | BOI Funds | DC |  | U | To be entrusted to NWSDB | 15/05/2024 | 30/09/2024
| Sub Total | 25 |  | 20
78.04 | Power Supply
78.04.001 | Internal power supply Scheme (HT/LT lines) . | 140 |  | 10 | BOI Funds | DC |  | P | To be entrusted to CEB | 2024-02-05 | 29/11/2024
| Sub Total | 140 |  | 10
78.08 | Fencing
78.08.001 | Construction of electric fence around Gloves International (PVT) Ltd . | 9 |  | 7.5 | BOI Funds | NCB | DPC | U | PC instructed to submit the issue paper to IFCC | 2023-04-08 | 15/10/2024 | 22/10/2024
| Sub Total | 9 |  | 7.5
78.09 | Miscellaneous
78.09.001 | Survey works, valuation and other consultancy charges. | 30 |  | 2 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
78.09.002 | Soil Investigation | 8 |  | 2 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
78.09.003 | Jungle Clearing , Removing high grown bushes, Cutting trees, etc. | 40 |  | 2 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 28/05/2024 | 2024-08-10 | 15/10/2024
78.09.004 | EIA Related works | 5 |  | 1 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
78.09.005 | Shifting/ refurbishment/related construction of utilities, etc | 5 |  | 5 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2024-12-02 | 2024-01-06 | 2024-07-06
78.09.006 | Temporary security points with sanitary facilities | 2 |  | 2 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 17/04/2024 | 24/07/2024 | 2024-01-08
| Sub Total | 90 |  | 14
78.11 | Land acquisition
78.11 | Land acquisition | 150 |  | 100 | BOI Funds | DC |  | P | To be done as required | 2024-01-01 | 31/12/2024
| Sub Total | 150 |  | 100
| Total Amount | 476 |  | 197.5
As at 01/01/2024

## FD
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Finance Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
50.13
50.13.004 | Providing record room facility for the Finance Department at Basement floor of SBJM Office | 8 | 5 |  | BOI Fund | NCB | DPC | U | Bids to be invited | 2023-03-04 | 31/05/2024 | 2024-07-06
| Total Amount | 8 | 5
As at 01/01/2024

## IT
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Equipment for Information Technology Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
76.09 | Miscellaneous
76.09.008 | Hyper Converged Infrastructure (Virtualization solution) | 70 |  | 70 | BOI Funds | NCB | DPC | U | Preparing RFP | 23/08/2023 | 27/06/2024 | 2024-03-07
76.09.009 | SD-WAN Phase II | 3.5 |  | 3.5 | BOI Funds | LNB | DPC | U | Requirement gathering stage | 2024-01-07 | 31/12/2024
76.09.003 | New DR site implementation | 18 |  | 18 | BOI Funds | NCB | DPC | U | Preparing RFP | 23/08/2023 | 27/06/2024 | 2024-03-07
76.09.004 | New Data Backup system | 15 |  | 15 | BOI Funds | NCB | DPC | U | Preparing RFP | 23/08/2023 | 27/06/2024 | 2024-03-07
76.09.010 | Modifications to the Server room of IT Department (i) Installation of Novec 1230 fire Suppression system (ii) Improving electrical system. | 12 | 12 |  | BOI Funds | NCB | DPC | U | Requirement gathering stage | 2024-01-07 | 31/12/2024
| Total Amount | 118.5 | 12 | 106.5
As at 01/01/2024

## CON
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Contingencies - Urgent Mechanical/Electrical/Plant and Equipment
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs.Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
77.09 | Miscellaneous
77.09.001 | Fixed asset purchasing for emergency/unforeseen repair works such as water, wastewater related pumps,motors ,electrical apparatus etc. | 13 |  | 5 | BOI Funds | NCB | DPC | U | To be done as required | 2024-02-01 | 31/12/2024
77.09.003 | Activities related to Eco Industrial Park concept including designs, researches and implementation, etc | 50 |  | 5 | BOI Funds | NCB | DPC | U | To be done as required | 2024-02-01 | 31/12/2024
| Total Amount | 63 |  | 10
As at 01/01/2024

## ENV
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Equipment for Environment Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
50.1 | Others
50.10.008 | Equipment for Environment Department | 6.4 | 2 |  | BOI Funds | NCB | DPC | P | To be purchased when need arises | 15/02/2024 | 31/07/2024 | 2024-07-07
50.10.009 | Upgrading,Testing facilities of Environment Laboratory (HEPZ) | 3.7 | 2 |  | BOI Funds | NCB | DPC | P | To be purchased when need arises | 15/02/2024 | 31.07.2024 | 2024-07-07
50.10.010 | Upgrading Environment monitoring facilities ( KIP,KgEPZ,MjEPZ) | 3 | 2 |  | BOI Funds | NCB | DPC | P | To be purchased when need arises | 15/02/2024 | 31.07.2024 | 2024-07-07
| Total Amount | 13.1 | 6
As at 01/01/2024

## ADMIN
Procurement Plan
Procurement Plan for year 2024
Ministry of Investment Promotion
Board of Investment of Sri Lanka
Capital Expenditure Under Administration Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Financial Allocation for 2024 as per approved Capital Budget (Inc. SSCL) (Rs. Mn) (Exc.VAT) |  | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
|  |  | Budget for rehabilitation/ upgrading of existing facilities | Budget for new investment
50.12 | Purchase of motor vehicles
50.12.032 | Purchase of 02 Nos Motorcycles and 02 nos Utility vehicles (01 nos Gully bowser & 01 nos water bowser) | 38 |  | 20 | BOI Funds | LNB/NCB | DPC | U | Quotations to be invited | 28/03/2024 | 30/09/2024 | 2024-06-10
| Sub Total | 38 |  | 20
49.05 | Building
49.05.039 | Providing steel filing racks, door access control system & 02 nos cctv camera installation to established 02 nos filing rooms of Investment Appraisal Department | 5 | 5 |  | BOI Funds | NS | DPC | U | Planning and estimation to be commenced | 25/03/2024 | 28/06/2024 | 2024-05-07
49.05.037 | Refurbishment of 24th , 26th & 8th floors *Level -24 (Work includes interior development, carpeting,electrical, telephone, network cabling, etc). *Level -26 (Work includes interior development & carpeting) * level 8th carpeting. | 15 | 5 |  | BOI Funds | NCB/ NS | DPC | P | Planning and estimation to be commenced | 28/03/2024 | 25/09/2024 | 2024-02-10
49.05.035 | Refurbishment of BOI Auditorium (Consultancy/Construction) | 50 | 2 |  | BOI Funds | NCB | DPC | P | Planning stage | 18/03/2024 | 16/12/2024 | 23/12/2024
| Sub Total | 70 | 12
49.1 | Others
49.10.038 | Supply, installation, commissioning and maintaining of surveillance camera systems to BEPZ | 5 |  | 5 | BOI Funds | NCB/ NS | DPC | U | Preparing Bidding document | 2023-01-12 | 28/03/2024 | 2024-03-04
| Sub Total | 5 |  | 5
| Total Amount | 113 | 12 | 25
As at 01/01/2024