## Summary
Procurement Plan - Content
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Summary Sheet
No | Name of the Zones, Industrial Parks , Special Projects Etc | Page Number
A | Existing Zones
1 | Katunayake Export Processing Zone | 04,05
2 | Biyagama Export Processing Zone | 06
3 | Koggala Export Processing Zone | 07
4 | Kandy Industrial Park | 08
5 | Malwatta Export Processing Park | 09
6 | Mirigama Export Processing Zone | 10
7 | Wathupitiwela Export Processing Zone | 11
8 | Horana Export Processing Zone | 12
9 | Mawathagama Export Processing Zone | 13
10 | Polgahawela Export Processing Zone | 14
11 | Mirijjawila Export Processing Zone | 15
12 | Seethawake Export Processing Zone | 16,17
13 | Proposed Industrial Zone Wagawatta | 18
B | New Zones
14 | Preliminary work of sites identified for new Zones. | 19
15 | Bingiriya Export Processing Zone | 20
16 | Textile Manufacturing Zone at Eravur,Batticaloa | 21
17 | Pharmaceutical Manufacturing Zone at Arabokka. | 22
18 | Site Identified for Arabokka Heavy Industry Zone | 23
C | Others
19 | Administration Department | 24
20 | Equipment for Information Technology Department | 25
21 | Contingencies - Urgent Mechanical/Electrical/Plant and Equipment. | 26
22 | Equipment for Environment Management Department | 27

## Acronyms
ACRONYMS
ICB | International Competitive Bidding
LIB | Limited International Bidding
LND | Limited National Bidding
NCB | National Competitive Bidding
NS | National Shopping
RPC | Regional Procurement Committee
DPC | Department Procurement Committee
MPC | Ministry Procurement Committee
CAPC | Cabinet Appointed Procurement Committee
DCPC | Department Consultant Procurement Committee
CWWPT | Common Wastewater Treatment Plant
WTP | Water Treatment Plant

## PP2025
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka

## KEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Katunayake Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
01.01.027 | Improvement of drain from Elsteel (Pvt)Ltd to Trinity steel stores at phase I . | 15 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2025-01-02 | 15/06/2025 | 2025-01-07
01.02.031 | Re-laying deteriorated water distribution lines at Ring road 01 and spur road 2 , phase 1 | 150 | BOI Funds | NCB | DPC | U | Re estimation | 19/10/2024 | 15/06/2025 | 30/06/2025
01.02.038 | Supply and Installation of 03 nos submersible tube well pumps | 5 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2025-01-02 | 15/07/2025 | 30/07/2025
01.03.028 | Supply and Installation of 02 nos submersible pumps for phase I lift station | 20 | BOI Funds | NCB | DPC | U | Draft bid document submitted for PC approval | 2024-02-09 | 2025-01-03 | 15/03/2025
01.03.029 | Supply and installation of 02nos progressive cavity pumps for CWWTP | 4 | BOI Funds | NCB | DPC | P | Estimate to be prepared by NWS & DB | 2024-01-11 | 15/03/2025 | 30/03/2025
01.03.026 | Supply,laying and commissioning of wastewater disposal pumping line form Phase lV to CWWTP | 150 | BOI Funds | NCB | DPC | p | Estimate to be prepared by NWS & DB | 2024-01-09 | 15/09/2025 | 2025-01-10
01.03.027 | Supply and installation of screw type belt press machine | 15 | BOI Funds | NCB | DPC | U | Estimate to be prepared by NWS & DB | 15/02/2025 | 2025-01-06 | 15/06/2025
01.04.015 | Rearrange of power supply connections to Administration building,Plaza unit 01 to 06 Fire unit and gate 01 | 42 | BOI Funds | NCB | DPC | U | Requested CEB to submit an estimate | 25/10/2024 | 16/04/2025 | 2025-02-05
01.04.016 | Supply and installation of 02 nos 22KW VFD panels including Sensor based PLC operation of 12 nos aerators at CWWTP | 13 | BOI Funds | NCB | DPC | U | Quotation called for VFD & comprehensive Chartered Engineer's inspection report requested from National Water Supply and Drainage Board | 25/10/2024 | 20/04/2025 | 2025-02-05
01.04.017 | Supply and installation of Solar power generation system for Gate 01 and Gate 04 of BOI-KEPZ. | 30 | BOI Funds | NCB | DPC | U | Bid evaluation | 2024-01-03 | 15/02/2025 | 30/03/2025
01.04.018 | Supply and installation 05nosAir conditioners plaza units | 2 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 15/01/2025 | 15/03/2025 | 15/05/2025
01.04.019 | Supply and installation of Solar power generation system for plaza buildings of BOI-KEPZ. | 90 | BOI Funds | NCB | DPC | U | Estimate to be prepared | 2025-01-02 | 2025-08-06 | 2025-01-07
01.05.052 | Repair of Fire Unit at Gate 1 (VIP Entrance) | 8 | BOI Funds | NCB | DPC | P | Contract to be award | 2024-01-04 | 2024-05-12 | 20/12/2024
01.05.057 | Partition of Engineering, IR, Finance, Visa & Audit Depts. at Plaza buildings | 18 | BOI Funds | NCB | DPC | U | Bid evaluation | 2024-01-02 | 2024-10-12 | 31/12/2024
01.05.054 | Construction of compost yard | 8.5 | BOI Funds | NCB | DPC | U | Contract to be award | 2024-01-06 | 2024-10-12 | 23/12/2024
01.05.056 | Rectification & Renovation of plaza buildings 3 to 6 | 10 | BOI Funds | NCB | DPC | P | Document evaluation report Re submit for PC approval | 2024-02-09 | 30/03/2025 | 2025-12-04
01.02.059 | Rectification & Renovation of plaza buildings 15 to18 | 10 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 15/12/2024 | 30/03/2025 | 2025-12-04
01.05.058 | Waterproofing of Administration building | 2.5 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 17/12/2024 | 15/03/2025 | 2025-01-04
01.08.012 | Supply and installation of 05 nos gates | 5 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 17/12/2024 | 15/03/2025 | 2025-01-04
As at 02/12/2024

## BEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Biyagama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
02.01.024 | Construction of storm water drains along the internal road of Block A & B and RCC box culvert of Block A at BEPZ | 24 | BOI Funds | NCB | DPC | U | Bid re -issuing | 2024-12-08 | 16/02/2025 | 23/02/2024
02.01.025 | Construction of vehicle park, boundary wall, drains & gates for Permit office & Daycare center at BEPZ | 73 | BOI Funds | NCB | DPC | U | Dept. estimate is being scrutinized | 2024-02-10 | 2025-02-04 | 16/04/2025
02.02.007 | Supply & Installation of dual suction volute pump for booster pump house at BEPZ | 6 | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 24/03/2025 | 21/07/2025 | 28/07/2025
02.02.008 | Consultancy for augmentation of 1000 m3/day WTP | 2 | BOI Funds | DC |  | U | To be entrusted to NWS&DB | 2025-01-03 | 2025-01-06 | 15/06/2025
02.03.035 | Augmentation of CWWTP-BEPZ - Consultancy | 25 | BOI Funds | DC |  | U | Planning | 20/02/2025 | 30/08/2025 | 15/09/2025
02.03.036 | Design Consultancy for improvement to wastewater Pump house at Block-B, BEPZ | 5 | BOI Funds | DC |  | P | Planning | 2025-05-01 | 15/05/2025 | 2025-01-06
02.04.009 | Supply & Installation of 250 kVA Generator to Administration Building BEPZ | 27 | BOI Funds | NCB | DPC | P | Bid Evaluation | 2024-01-07 | 2024-09-12 | 16/12/2024
02.04.011 | Improvements to the existing Street Light network with HT & LT bundle cables & poles of internal Roads at Block ‘B’ BEPZ | 5 | BOI Funds | DC |  | P | Estimate to be obtain from CEB |  |  | 2025-02-04
02.04.012 | Supply & Installation of 150W LED Street Light network of internal Roads at Block ‘A’ BEPZ | 22 | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared by CEB | 2025-05-02 | 2025-11-06 | 18/06/2025
02.05.023 | Construction of Security / Plant operator Room for Lift Station of KRB in CWWTP at BEPZ | 6 | BOI Funds | NCB | DPC | p | Bids invited | 30/08/2024 | 30/12/2024 | 2025-05-01
02.05.025 | Improvement to the two storied Fire & Security Building at BEPZ | 18.5 | BOI Funds | NCB | DPC | p | Dept. estimate to be prepared | 2025-03-03 | 15/07/2025 | 2025-01-08
02.05.027 | Supply & Installation of 08 Nos Split type Air-conditioning to Admin Building & Control room at BEPZ | 4 | BOI Funds | NCB | DPC | U | Dept. estimate to be prepared | 2025-10-02 | 20/06/2025 | 30/06/2025
02.05.028 | Construction of new material receiving building at dump yard, BEPZ | 25 | BOI Funds | NCB | DPC | p | Dept. estimate to be prepared | 2025-01-02 | 25/08/2025 | 2025-05-06
As at 02/12/2024

## KgEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Koggala Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
03.02.018 | Construction of 1000m3 capacity ground water sump | 128 | BOI Funds | NCB | DPC | U | Estimation & preparation of tender documents is to be prepared at NWSDB | 2025-01-02 | 2025-03-08 | 15/8/2025
03.03.016 | Construction of new sea outfall line | 105.31 | BOI Funds | NCB | DPC | U | Contract to be award | 2021-01-06 | 2024-05-12 | 16/12/2024
03.03.030 | Repairs to the Package Treatment Plant including the consultancy charges of NWSDB | 10 | BOI Funds | NCB | DPC | U | NWSDB was requested to inspected condition of the plant before re estimating | 2025-01-01 | 13/7/2025 | 20/7/2025
03.03.032 | Supplying & implementation of lightning protection system for the sewerage pump houses | 8.4 | BOI Funds | NCB | DPC | N | Required details for the design & preparation of estimates submitted to NWSDB | 2025-01-03 | 24/7/2025 | 2025-01-08
03.05.025 | Installation of solar panels to Custom & security Building | 7 | BOI Funds | NS | DPC | N | Preparation of estimates in progress | 13/11/2024 | 17/4/2025 | 2025-01-05
03.05.026 | Replacing of 04 nos. of air condition units at the Admin. Complex building | 1.8 | BOI Funds | NS | RPC | N | Estimates to be prepared | 2025-01-03 | 2025-01-06 | 2025-08-06
03.08.010 | Construction of part of the perimeter fence from custom & security building upto ground water tower at KgEPZ(400.0m) | 10 | BOI Funds | NCB | DPC | U | Preparation of bidding documents to submit the PC for approval | 2024-02-09 | 30/3/2025 | 18/4/2025
03.08.011 | Construction of balance part of the perimeter fence from custom & security building upto the gate at P7P2A road at KgEPZ(Approx. 600m) | 15 | BOI Funds | NS | DPC | U | Estimates to be prepared | 2025-01-01 | 20/05/2025 | 2025-01-06
As at 02/12/2024

## KIP
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Kandy Industrial Park
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
04.01.016 | Construction of access road including retaining wall & culvert to lot nos. 03 & 04. | 30 | BOI Funds | NCB | DPC | U | Estimating | 28/11/2024 | 2025-10-04 | 27/05/2025
04.05.010 | Construction of a building for Fire Department. | 1.5 | BOI Funds | NCB | DPC | U | Recalling of bid | 2024-12-08 | 30/12/2024 | 15/01/2025
04.05.012 | Construction of Plant Operator Room with Sanitary Facilities. | 3.5 | BOI Funds | NCB | DPC | U | Bids invited | 2024-12-08 | 15/01/2025 | 22/01/2025
04.05.013 | Construction of a utility building, vehicle garage & improvements to existing driver rest room building. | 30 | BOI Funds | NCB | DPC | U | Planning | 2025-05-01 | 15/05/2025 | 2025-01-06
04.09.009 | Supply, installation ,commissioning and maintenance of nos 08 of surveillance CCTV cameras to cover the zone entrance. | 2 | BOI Funds | NCB | DPC | U | Recalling of bid | 23/08/2024 | 30/01/2025 | 2025-07-02
04.09.010 | Survey works, valuation and other consultancy charges | 2 | BOI Funds |  | DC | N | To be done as required | Procurement will be initiated when need arise
04.09.014 | Installation solar panels for power generation on office building. | 6 | BOI Funds | NCB | DPC | U | Estimating | 22/08/2024 | 30/03/2025 | 2025-10-04
04.09.015 | Supplying & fixing fire hydrants. | 4 | BOI Funds | NCB | DPC | P | Planning | 31/01/2025 | 20/05/2025 | 2025-05-06
04.11.001 | Land Development for 14 Ac. land (KTI). | 5 | BOI Funds | NCB | DPC | U | To be done as required | Procurement will be initiated when need arise
As at 02/12/2024

## MEPP
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Malwatta Export Processing Park
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
05.05.015 | Consultancy for Modification of Steel Roof Structure for BOI Admin Building & Security Checkpoint Area for Installation of Solar Panels Including Colour Washing to the Roofs of BOI Admin Complex | 0.5 | BOI Funds | NS | DC | P | Consultancy to be entrusted | 2025-02-01 | 2025-01-03 | 2025-07-03
05.05.016 | Modification of Steel Roof Structure for BOI Admin Building & Security Checkpoint Area for Installation of Solar Panels Including Colour Washing to the Roofs of BOI Admin Complex | 4 | BOI Funds | NCB | DPC | P | Estimates to be prepared . | 30/03/2025 | 25/06/2025 | 2025-02-07
05.08.006 | Repairing of Chain Link Fence with Removing & Replacing of Damaged Concrete Post. | 2 | BOI Funds | NS | DPC | P | Estimates to be prepared . | 2025-01-02 | 20/05/2025 | 2025-02-06
05.09.013 | Design and Installation of Solar Panel System for WWTP | 6 | BOI Funds | NCB | DPC | P | Estimates to be prepared . | 16/01/2025 | 2025-11-05 | 16/05/2025
As at 02/12/2024

## MEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Mirigama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
06.01.044 | construction of access road to water treatment plant. | 17 | BOI Funds | NCB | DPC | U | Estimates to be prepared | 2025-01-03 | 2025-01-06 | 15/06/2025
06.02.019 | Supply, installation & Commissioning of high lift pumps for Water treatment plant. | 29.5 | BOI Funds | NCB | DPC | U | Bids invited | 2024-01-10 | 2025-01-02 | 15/02/2025
06.03.013 | Supplying & Laying of Sewerage Collecting network and construction of lift wells in block A of MEPZ. | 163 | BOI Funds | NCB | DPC | U | Bid evaluation | 15/02/2023 | 30/01/2025 | 15/02/2025
06.03.012 | Repair and service of M & E works in WWTP. | 21 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 15/09/2025 | 15/12/2025 | 20/12/2025
06.04.002 | Fixing of lighting arrestor system to administration building. | 2.5 | BOI Funds | NCB | DPC | U | Contract to be award | 2024-02-09 | 2025-01-01 | 2025-10-01
06.04.009 | Supply & commissioning of 150KVA generator for water intake. | 13 | BOI Funds | NCB | DPC | U | Draft bid document submitted for PC approval | 13/09/2024 | 15/03/2025 | 25/03/2025
06.05.025 | Design and construction supervision of Construction of extension to the administration building.( with a conference room.) | 1 | BOI Funds | DC |  | P | Design & Consultancy to be entrusted | 2025-02-01 | 2025-01-03 | 2025-07-03
06.05.024 | Construction of extension to the workers rest room. | 5 | BOI Funds | NCB | DPC | U | Contract to be award | 2024-01-07 | 2024-10-12 | 17/12/2024
06.05.026 | Design and construction supervision of Construction of shelters for security entrance gates. | 0.9 | BOI Funds | DC |  | P | Design & Consultancy to be entrusted | 2025-01-02 | 30/03/2025 | 2025-10-04
06.05.027 | Construction of shelters for security entrance gates in Block A and B. | 12 | BOI Funds | NCB | DPC | P | Designing to be done | 2025-01-07 | 2025-01-10 | 2025-10-10
06.09.024 | Supplying, installation, testing and commissioning of BOI building’s roof top mounted 40Kw solar photovoltaic systems at MEPZ. | 6.5 | BOI Funds | NCB | DPC | P | Bid evaluation | 2024-01-10 | 15/02/2025 | 25/02/2025
As at 02/12/2024

## WEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Wathupitiwala Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
07.01.018 | Rehabilitation of zone entrance road including drains , walkways up to main entrance from Kandy road. | 25 | BOI Funds | DC | DPC | P | Request Estimate from PRDA . | 2024-12-11 | 15/02/2025 | 2025-01-03 | Project to be implemented through PRDA
07.03.025 | Replacing of damaged section of sewer collection line along kittammahara road at wastewater treatment scheme -WEPZ. | 2 | BOI Funds | NS | DPC | U | Estimation to be commenced | 20/12/2024 | 2025-10-04 | 25/04/2025
07.04.001 | Supply and installation of Solar power generation system for BOI buildings. | 15 | BOI Funds | NCB | DPC | P | Estimate to be revised | 2024-04-12 | 30/03/2025 | 2025-10-04
07.05.032 | Improvements to security buildings at main entrance of Block -A | 8.25 | BOI Funds | NCB | DPC | P | Draft bid document submit for PC approval | 2024-01-07 | 2024-03-12 | 2024-10-12
07.05.034 | Construction of quarters at upper floor of Admin Dept | 3.65 | BOI Funds | NCB | DPC | P | Estimate is in the process of approval | 14/07/2024 | 2024-09-12 | 15/12/2024
07.05.036 | Modifying of pantry area of admin building for a environment laboratory | 10 | BOI Funds | NCB | DPC | U | Planning and estimation to be commence | 2025-01-01 | 30/04/2025 | 2025-05-05
07.09.013 | Installation of CCTV surveillance system at all gates of WEPZ | 2 | BOI Funds | NCB | DPC | N | Planning and designing to be commenced | 2025-02-02 | 25/05/2025 | 2025-01-06
As at 02/12/2024

## HEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Horana Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
08.01.036 | Improvement of access road of the Zone | 50 | BOI Funds | NCB | DPC | U | Estimates to be prepared | 2025-10-01 | 2025-10-05 | 25/05/2025
08.01.037 | Construction of Bridge at the access road of water Intake of water supply scheme/consultancy | 20 | BOI Funds | NCB | DPC | N | Planning | 2025-10-01 | 15/06/2025 | 2025-01-07
08.02.036 | Augmentation of water treatment plant- construction & consultant. | 841 | BOI Funds | NCB | CAPC | U | Bidding Document evaluation | 2021-01-01 | 28/05/2025 | 19/06/2025
08.02.040 | Design, Supply, Installation and Commision of Floating type Intake. | 200 | BOI Funds | NCB | DPC | U | Bid evaluation | 2021-07-12 | 30/01/2025 | 21/02/2025
08.02.042 | Supply Installation 01 no. Submersible Pump with motor for pontoon 02 & 02 nos. Submersible Pumps for pontoon 01 | 4.2 | BOI Funds | NCB | DPC | U | Bidding Document evaluation | 2024-11-10 | 15/02/2025 | 2025-01-03
08.02.043 | Supply of 04 nos.chemical dosing pumps for water treatment plant. | 1.5 | BOI Funds | NCB | DPC | U | Bidding document evaluation | 2024-09-02 | 30/03/2025 | 2025-07-04
08.03.021 | Augmentation of CWWTP-construction | 1100 | BOI Funds | NCB | CAPC | P | Contract to be award | 2021-01-03 | 2024-02-12 | 20/12/2024
08.03.035 | Construction of wetland system | 7 | BOI Funds | NCB | DPC | P | Re submission of Bidding document for PC approval | 2024-01-10 | 15/02/2025 | 22/02/2025
08.05.021 | Construction of security room at Gate 2 and construction of Security gate security room near the CEB Grid. | 5 | BOI Funds | NCB | DPC | U | Estimate is in the process of approval | 15/11/2024 | 30/04/2025 | 2025-07-05
08.05.023 | Installation of surge arrester for Administration Building & Wastewater Treatment Plant. | 3.5 | BOI Funds | NS | DPC | U | Estimating | 2024-06-11 | 30/05/2025 | 2025-07-06
08.09.003 | Survey work | 1 | BOI Funds | DC |  | P | To be done as required | Procurement will be initiated when need arise
As at 02/12/2024

## MwEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Mawathagama Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
09.02.026 | Improvement of Water Treatment Plant | 2 | BOI Funds | NS | DPC | P | Estimate preparation stage | 13/11/2024 | 15/04/2025 | 20/04/2025
09.09.013 | Spare pumps for Wastewater treatment plant. -02 nos. | 7.5 | BOI Funds | NCB | DPC | U | Estimate is in the process of approval. Document preparation stage | 15/03/2024 | 30/03/2025 | 2025-10-04
09.09.011 | Supplying & Installation of a 20 kwh Solar PV systems for BOI Administration building rooftop. | 5 | BOI Funds | NCB | DPC | P | Estimate preparation stage | 15/08/2024 | 15/03/2025 | 25/03/2025
As at 02/12/2024

## PwEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Polgahawela Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
10.03.014 | Improvements to the Waste water treatment Plant at Polgahawela EPZ. (Design and Consultancy ) | 2 | BOI Funds | DC |  | U | Design stage | 2024-01-10 | 2025-01-06 | 16/06/2025
10.03.015 | Improvements to the Waste water treatment Plant at Polgahawela EPZ. | 20 | BOI Funds | NCB | DPC | U | Design stage | 15/03/2025 | 15/09/2025 | 30/09/2025
10.05.007 | Construction of an extension of Admin building with conference room. | 7 | BOI Funds | NCB | DPC | U | Preparation Bidding document | 2024-02-09 | 15/02/2025 | 2025-01-03
10.09.014 | Supplying and installation of a 10 kw solar PV systems for BOI building's rooftop at Polgahawela Export Processing Zone. | 2 | BOI Funds | NS | DPC | U | Preparation Bidding document | 2024-02-09 | 15/02/2025 | 2025-01-03
As at 02/12/2024

## MjEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Mirijjawila Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
13.01.016 | Rectification of damaged sections of Existing Main Entrance Road CH 0+00 to CH 0+218 | 28.54 | BOI Funds | NCB | DPC | N | Revised estimate is in the process of approval | 2024-02-03 | 30/03/2025 | 21/04/2025
13.01.017 | Construction of Road Drains along New RN boundary road up to Lanwa | 25 | BOI Funds | NCB | DPC | N | Estimates to be prepared | 2025-01-03 | 30/06/2025 | 21/07/2025
13.02.007 | Improvements to the Existing Water Tower & Sump | 25 | BOI Funds | NCB | DPC | N | Bids invited | 30/03/2024 | 2025-01-04 | 2025-01-05
13.05.010 | Security & gate facilities at New Main Entrance along RN Boundary | 2.5 | BOI Funds | NCB | DPC | N | Revised estimate is in the process of approval | 31/01/2024 | 30/04/2025 | 14/05/2025
13.05.011 | Supply & installation of Generator for Admin Office building | 7 | BOI Funds | NCB | DPC | N | Revised estimate is in the process of approval | 15/02/2024 | 2025-01-05 | 22/05/2025
13.08.010 | Repairing the damaged sections of existing boundary fence(Old & New Zonal) | 24 | BOI Funds | NCB | DPC | N | Revised estimate is in the process of approval | 18/06/2024 | 15/05/2025 | 2025-06-06
13.09.010 | Survey works, valuation and other consultancy charges. | 2.5 | BOI Funds |  |  |  | To be done as required | Procurement will be initiated when need arise
13.09.031 | Shifting/ refurbishment/related construction of utilities, services improvements rehabilitation by other agencies (RDA/NWS&DB/CEB/SLT,Etc) | 5 | BOI Funds
As at 02/12/2024

## SEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Seethawake Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
23.02.025 | Supply & Installation of the reservoir outlet valve (450 mm Diameter.) | 4 | BOI Funds | NCB | DPC | U | Bid evaluation | 2024-01-01 | 30/01/2025 | 2025-07-02
23.02.026 | Rectification of the defects in the package water treatment plant | 6 | BOI Funds | NCB | DPC | U | Contract to be award | 2024-01-01 | 2024-11-12 | 16/12/2025
23.02.028 | Modification of the Chlorine safety system | 10 | BOI Funds | NS | DPC | U | Bids invited | 2024-01-06 | 2025-05-02 | 20/02/2025
23.02.029 | Purchasing of portable Mud removing motor | 2 | BOI Funds | NS | DPC | N | Bids invited | 2024-01-06 | 2025-05-02 | 20/02/2025
23.02.030 | Augmentation of water treatment plant 5000m3 (Consultancy fee for design) | 2 | BOI Funds | DC |  |  | Designing Stage | 2024-01-06 | 2025-03-03 | 2025-10-03
23.02.031 | Supply & laying of DI Pipe line for raw water intake well to WTP at SEPZ | 15 | BOI Funds | NCB | DPC | U | Designing Stage | 2024-01-06 | 2025-01-04 | 25/04/2025
23.02.036 | Supply & Installation of raw water pumps with Accessories for Intake well | 15 | BOI Funds | NCB | DPC | U | Bid evaluation | 2024-01-06 | 30/12/2024 | 14/01/2025
23.02.032 | Augmentation of water treatment plant 5000m3 (Contract ) | 200 | BOI Funds | NCB | DPC | U | Designing Stage | 2025-01-04 | 2025-03-10 | 25/10/2025
23.02.033 | Supply and Installation of secion valves to main distribution line (Diameter appx. 450 mm),Construction of washout valve at near the main gate at SEPZ Modification of alum/lime Chemical dosing system WTP | 6 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-01 | 2025-03-03 | 15/03/2025
23.02.034 | Fabricating of pantry cupboard at laboratory area at WTP | 1.5 | BOI Funds | NS | DPC | N | Estimates to be prepared | 01/012025 | 2025-01-04 | 25/04/2025
23.02.035 | Construction of restroom for Resident Engineer -NWS&DB | 6 | BOI Funds | NCB | DPC | N | Design stage | 20/11/2024 | 2025-02-04 | 2025-10-04
23.03.029 | Supply and installation of treated wastewater discharge line extension utilizing DI pipes & fittings including payment to NWS&DB | 10 | BOI Funds | NCB | DPC | P | Design stage | 26/06/2024 | 2025-01-04 | 2025-10-04
23.05.040 | Construction of Stores Building at admin building at SEPZ,Construction of Vehicle shed for Waterwater Bowser,Repairing of roof at Dehydrator building at WWTP,Renovation of wash room at Administrative premises , Construction of VIP Washroom at admin building at SEPZ,Construction of Wash room for permit office (outsiders ) at SEPZ | 17 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-01 | 2025-04-04 | 25/04/2025
23.05.041 | Supply & ins. of AC unit for auditorium at administrative building | 4 | BOI Funds | NS | DPC | N | Estimates to be prepared | 2025-01-01 | 2025-03-03 | 15/03/2025
23.05.042 | Construction of a dining area for the use for Auditorium at SEPZ | 1 | BOI Funds | NS | DPC | N | Estimates to be prepared | 2025-01-01 | 2025-03-02 | 15/02/2025
23.05.044 | Construction of balance part of the day care center building | 33 | BOI Funds | NCB | DPC | N | Estimates to be prepared | 15/01/2025 | 30/04/2025 | 14/05/2025
23.05.043 | Consultancy/contract renovation of water leakage for admin building roof slab area and roof structure | 10 | BOI Funds | NCB | DPC | N | Estimates to be prepared | 30/01/2025 | 2025-04-04 | 28/04/2025
23.09.061 | Supply and Installation of Auto barrier gate at Main Entrance | 4 | BOI Funds | NCB | DPC | N | Estimation | 24/06/2024 | 15/03/2025 | 22/03/2025
23.09.062 | Supply and Installation of Solar PV Generation System at SEPZ | 30 | BOI Funds | NCB | DPC | P | Bids invited | 24/06/2024 | 14/05/2025 | 25/05/2025
23.09.063 | Construction of Sludge pit at SEPZ | 10 | BOI Funds | NS | DPC | P | Estimates to be prepared | 2025-01-01 | 2025-10-03 | 25/03/2025
23.09.064 | Purchasing of lab Equipments | 15 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-01 | 2025-01-06 | 2025-10-06
23.09.065 | Supply and installation AC units for WTP office Building | 3 | BOI Funds | NS | DPC | N | Estimates to be prepared | 2025-01-01 | 14/03/2025 | 20/03/2025
23.09.066 | Erection of steel barriers for Internal road at SEPZ ,Erection of steel wicket gates at SEPZ ,Construction of steel security hut | 4 | BOI Funds | NS | DPC | N | Estimates to be prepared | 2025-01-01 | 14.02.2025 | 20.04.2025
As at 02/12/2024

## WIZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Wagawatta Industrial Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
33.01.022 | Construction of internal road to the Grid substation | 40 | BOI Funds | NCB | DPC | N | Planning | 2025-01-03 | 30/07/2025 | 15/08/2025
33.02.007 | Extension of existing water supply pipeline | 10 | BOI Funds | NCB | DPC | N | Planning | 2025-01-04 | 20/08/2025 | 15/09/2025
As at 02/12/2024

## NZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Preliminary work of sites identified for new Zones. (Kankesanthurai,Paranthan,Keragale,Kandy, Mankulam, Kappalthurai, Iranawila, IT Parka, Etc)
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
69.01.006 | Preliminary access road construction work. | 100 | BOI Funds | NCB | DPC | P | To be done as required | Procurement will be initiated when need arise
69.02.008 | Initial Water Supply. | 900 | BOI Funds | DC |  | P | To be done as required | Procurement will be initiated when need arise
69.02.009 | Ground water investigation | 20 | BOI Funds | DC |  | P | To be done as required
69.04.007 | Initial Power supply by CEB. | 10 | BOI Funds | DC |  | P | To be done as required | Procurement will be initiated when need arise
69.05.010 | Temporary site offices for new zones | 10 | BOI Funds | NCB | DPC | P | To be done as required | Procurement will be initiated when need arise
69.05.011 | Temporary security points with Sanitary Facilities for new Zones | 5 | BOI Funds | NCB | DPC | P | To be done as required
69.08.010 | Construction of a perimeter fence. | 500 | BOI Funds | NCB | DPC | P | To be done as required | Procurement will be initiated when need arise
69.09.020 | Survey works, valuation and other consultancy charges. | 20 | BOI Funds | DC |  |  | To be done as required | Procurement will be initiated when need arise
69.09.021 | Soil Investigations. | 10 | BOI Funds | DC |  | P | To be done as required
69.09.022 | Jungle clearing, removing high grown bushes, cutting trees ,etc. | 20 | BOI Funds | NCB | DPC | P | To be done as required
69.09.023 | EIA Related works | 40 | BOI Funds | DC |  | P | To be done as required
69.09.024 | Selection of an appropriate consultancy firm for the feasibility studies of New investment Zones proposed by the Cabinet Decision | 23 | BOI Funds | DC |  | N | To be done as required
69.09.025 | Shifting/ refurbishment/related construction of utilities, services improvements rehabilitation by other agencies (RDA/NWS&DB/CEB/SLT,Etc) | 10 | BOI Funds | DC |  | P | To be done as required
69.11.001 | Land Acquisition related works | 10 | BOI Funds | DC |  | P | To be done as required
As at 02/12/2024

## BgEPZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Bingiriya Export Processing Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
73.01.006 | Surfacing of Internal roads and Construction of Culverts at Bingiriya EPZ. | 150 | BOI Funds | NCB | DPC | P | Estimation commenced | 2024-01-11 | 2025-10-05 | 25/05/2025
73.01.007 | Improvement of storm water drains up to the Nelumwala Ela from the zone boundary. | 2 | BOI Funds | DC |  | U | Request estimate from Agrarian services. | 2024-10-10 | 30/12/2024 | 2025-10-01
73.02.005 | Extension of water distribution line upto lot no 06 at Bingiriya EPZ | 2 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-01 | 2025-01-04 | 2025-10-04
73.03.005 | Construction of Wastewater collection network at Bingiriya EPZ. | 100 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 15/01/2025 | 31/06/2025 | 14/07/2025
73.04.005 | Augmentation of existing 10MVA power supply up to 20MVA | 100 | BOI Funds | DC |  | U | Estimate to be obtained from CEB | 2025-01-01 | 2025-01-03 | 2025-10-03
74.05.010 | Construction of Administration building, Main gate building & Fire building at BgEPZ | 185 | BOI Funds | NCB | DPC | P | Design & Estimation to be commenced | 15/01/2025 | 2025-01-05 | 2025-01-06
73.08.003 | Construction of balance chainlink fence at BgEPZ | 10 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-04 | 2025-10-07 | 20/07/2025
73.08.004 | Construction of Barbed wire fence for the eastern boundary,critical section of BgEPZ | 20 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-05-01 | 2025-04-04 | 18/04/2025
73.08.005 | Construction of chainlink fence at entrance gate area, at BgEPZ (Phase II) | 140 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-05-01 | 30/04/2025 | 21/05/2025
As at 02/12/2024

## TMZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Textile Manufacturing Zone, – Punnakuda, Eravur, Batticaloa
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
74.01.011 | Construction of main internal road – Phase I (St. 0+000 to St. 0+130) | 45.4 | BOI Funds | NCB | DPC | U | PC approved the draft bidding document | 17/06/2024 | 15/03/2025 | 2025-10-04
74.02.004 | Construction of Permanent Internal Water Supply Scheme | 267.5 | BOI Funds | NCB | DPC | U | Design is completed. Estimate reviewing is in progress | 2024-02-01 | 15/06/2025 | 22/06/2025
74.02.007 | Construction of shallow well | 4 | BOI Funds | NS | DPC | P | Estimate is being preparing for cons. of first well to identify the hydro geological factors of ground water | 2024-02-02 | 21/05/2025 | 28/05/2025
74.03.003 | Construction of wastewater collection network | 876.5 | BOI Funds | NCB | CAPC | U | Pending Board approval for revised NWS&DB's charges | 2024-02-01 | 15/11/2025 | 2025-06-12
74.05.008 | Construction of proposed main entrance building | 93 | BOI Funds | NCB | DPC | U | SEC has submitted a preliminary design | 2024-01-11 | 15/06/2025 | 22/06/2025
74.09.001 | Survey works, valuation and other consultancy charges. | 2.5 | BOI Funds | DC |  |  | To be done as required | Procurement will be initiated when need arise
74.08.003 | Construction of Perimeter Fence (2.0 km) - stage III (along the balance length of the boundary 200 & 55.28 Acres Lands) | 50 | BOI Funds | NCB | DPC | U | Land acquisition is in progress | 2025-01-06 | 2025-01-10 | 21/10/2025
74.09.010 | Establishment of environment monitoring facilities | 5 | BOI Funds | NCB | DPC | U | To be done as required | Procurement will be initiated when need arise
As at 02/12/2024

## PMZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Pharmaceutical Manufacturing Zone at Arabokka
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
75.02.003 | Extension of 300 cum/day water supply line with in the phase 1 zone for construction supply including design consultancy. | 8 | BOI Funds | DC |  | P | To be entrusted to NWSDB | 2025-01-01 | 30/11/2025 | 15/12/2025
75.04.001 | Initial power supply | 15 | BOI Funds | DC |  | P | To be entrusted to CEB | 15/01/2025 | 30/11/2025 | 15/12/2025
75.09.004 | Survey works, valuation and other consultancy charges. | 5 | BOI Funds | DC |  | P | To be done as required | Procurement will be initiated when need arise
75.09.007 | EIA and IEA related works. | 1.5 | BOI Funds | DC |  | P
75.09.008 | Soil and groundwater investigation | 1 | BOI Funds | DC |  | P
75.09.009 | Shifting/ refurbishment/related construction of utilities, services improvements rehabilitation by other agencies (RDA/NWS&DB/CEB/SLT,Etc) | 5 | BOI Funds | DC |  | P
As at 02/12/2024

## HIZ
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Site Identified for Arabokka Heavy Industry Zone
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
78.01.002 | Preliminary gravel road construction work.(Stage II) | 32 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 15/3/2025 | 11/9/2025 | 2025-10-10
78.02.001 | Water supply/connections | 25 | BOI Funds | DC |  | P | To be entrusted to NWSDB | 30/05/2025 | 15/10/2025 | 2025-06-11
78.04.001 | Internal power supply Scheme (HT/LT lines) . | 100 | BOI Funds | DC |  | P | To be entrusted to CEB | 15/01/2025 | 30/06/2025 | 21/07/2025
78.09.001 | Survey works, valuation , feasibility charges and other consultancy charges. | 30 | BOI Funds | DC |  | P | To be done as required | Procurement will be initiated when need arise
78.09.002 | Soil Investigation | 8 | BOI Funds | DC |  | P
78.09.003 | Jungle Clearing , Removing high grown bushes, Cutting trees, etc. | 40 | BOI Funds | DC |  | P
78.09.004 | EIA Related works | 5 | BOI Funds | DC |  | P
78.09.007 | Shifting/ refurbishment/related construction of utilities, services improvements rehabilitation by other agencies (RDA/NWS&DB/CEB/SLT,Etc) | 5 | BOI Funds | DC |  | P
78.09.006 | Temporary security points with sanitary facilities | 2 | BOI Funds | NCB | DPC | P | Estimate to be prepared | 2025-01-05 | 29/08/2025 | 2025-12-09
78.09.008 | Planning and designing internal road by RDA | 5 | BOI Funds | DC |  | P | To be entrusted to RDA | 15/01/2025 | 30/06/2025 | 14/07/2025
As at 02/12/2024

## ADMIN
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Capital Expenditure Under Administration Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
50.12.032 | Purchasing of 01 nos Gully bowser, Tractor and 02 nos Motorcycles ,etc | 24 | BOI Funds | LNB/NCB | DPC | U | Document to be prepaired | 20/03/2025 | 15/05/2025 | 2025-06-06
50.12.033 | Purchase of 03 Nos fire engines with storage tanks | 100 | BOI Funds | LNB/NCB | DPC | U | Document preparation (Board already approved Rs. 55Mn to purchase Fire vehicles) | 25/03/2025 | 15/09/2025 | 2025-06-10
49.05.037 | Rearrangement of Floors - Work includes interior development, carpeting, electrical, telephone, network cabling, etc. *Level 24 - DG's Office, Investment Appraisal Department, *Level 26 - Chairman's Office, PI Department *Level - 27 - Legal Department *Level - 09 - HR & Administration * Level 08 - Finance Department *Level 24 - Installation of door access control system & Security camera to filing rooms | 15 | BOI Funds | NCB/ NS | DPC | P | Planning Process | 15/02/2025 | 20/10/2025 | 2025-04-11
45.05.061 | Expansions to the IFC unit. | 3 | BOI Funds | NCB/ NS | DPC | P | Designing stage | 2025-10-05 | 15/09/2025 | 2025-01-10
45.05.063 | Refurbishment of all Lunch rooms located in BOI owned floors | 6 | BOI Funds | NCB/ NS | DPC | P | Planning Process | 25/03/2025 | 20/11/2025 | 2025-04-12
49.05.035 | Refurbishment of BOI Auditorium (Consultancy/Construction) | 12 | BOI Funds | NCB/ NS | DPC | P | Designing stage | 15/01/2025 | 30/09/2025 | 21/10/2025
45.05.059 | Renovation of the BOI owned building at No. 14, Sir Baron Jayathilaka Mawatha *Renovation of entire roof of the BOI building *Establishing of a Central Record Room for BOI departments at the basement floor | 25 | BOI Funds | NCB | DPC | U | Document preparation | 15/02/2025 | 20/09/2025 | 2025-04-10
45.05.064 | Refurbishment of departments at WTC when arises a requirement | 5 | BOI Funds | NCB/ NS | DPC | P | As per the decision of management, planning process will be started | 20/01/2025 | 15/11/2025 | 30/11/2025
As at 02/12/2024

## IT
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Equipment for Information Technology Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
76.09.003 | New DR site implementation | 18 | BOI Funds | NCB | DPC | U | Pending PC approval for bid document | 20/08/2024 | 15/03/2025 | 26/03/2025
76.09.004 | New Data Backup system | 15 | BOI Funds | NCB | DPC | U | Pending PC approval for bid document | 20/08/2024 | 15/03/2025 | 26/03/2025
76.09.008 | Hyper Converged Infrastructure (Virtualization solution) | 117 | BOI Funds | NCB | DPC | U | Pending PC approval for bid document | 20/08/2024 | 15/03/2025 | 26/03/2025
76.09.010 | Modifications to the Server room of IT Department (i) Installation of Novac 1230 fire Suppression system (ii) Improving electrical system | 12 | BOI Funds | NCB | DPC | U | Bid to be invited | 20/08/2024 | 30/01/2025 | 2025-07-02
As at 02/12/2024

## CON
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Contingencies - Urgent Mechanical/Electrical/Plant and Equipment,etc
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
77.09.001 | Fixed asset purchasing for emergency/unforeseen repair works such as water, wastewater related pumps,motors ,electrical apparatus etc. | 30 | BOI Funds | BOI Funds | NCB | DPC | U | To be done as required | Procurement will be initiated when need arise
77.09.003 | Activities related to Eco Industrial Park concept including designs,researches and implementation etc | 50 | BOI Funds | BOI Funds | NCB | DPC | U | To be done as required
As at 02/12/2024

## ENV
Procurement Plan
Procurement Plan for year 2025
Ministry of Finance ,Planning and Economic Development
Board of Investment of Sri Lanka
Equipment for Environment Department
Department/ Line Agency/ Ministry (Budget line Item No.) | Procurement Category (Goods, Works & Services etc.) (Description of the work item) | Estimated Cost (Rs. Mn.) | Source of Financing | Procurement method (ICB,LIB,LNB,NCB and National Shopping etc.) | Level of Authority | Priority status U=Urgent P=Priority N=Normal | Current Status of procurement preparedness activities | Scheduled date of Commencement of Procurement (Pre Tender) (D/M/Year) | Scheduled date of Completion of Procurement (Pre Tender) (D/M/Year) | Tentative date of award (D/M/Year) | Remarks
50.10.008 | Equipment for Environment Department ,etc | 5 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 2025-01-01 | 15/10/2025 | 30/10/2025
50.10.009 | Upgrading,Testing facilities of Environment Laboratory (HEPZ) | 3.7 | BOI Funds | NCB | DPC | P | Contract to be award | 15/02/2024 | 15/01/2025 | 2025-01-02
50.10.010 | Upgrading Environment monitoring facilities (KIP,KgEPZ,MjEPZ) | 3 | BOI Funds | NCB | DPC | P | Contract to be award | 15/02/2024 | 15/01/2025 | 2025-01-02
50.10.011 | Equipment for Environment Departments at HEPZ,KEPZ, BEPZ,etc | 8.5 | BOI Funds | NCB | DPC | P | Estimates to be prepared | 15/01/2025 | 30/10/2025 | 14/11/2025
As at 02/12/2024